## Traceability matrix
User Requirement Specifications |  |  | Design Input Requirements |  | Verification |  |  |  | Validation
URS ID | URS | Importance [MUST / NICE TO HAVE] | DIR ID | DIR | Plan/method | Report result | Pass? [Y/N] | Comment | Plan / method | Report / result | Pass? [Y/N] | Comment
URS-01 | User wants to safely grip a bicycle handle to manouver it | MUST | DIR-01 | The device shall have a custom shape personalized for the user hand so that they can easily grip and hold on to the device which is mounted on the bike handle. | 3D design and modeling of the user hand with 3D scan | The user confirmed they could easily hold on to the custom-grip. | Y |  | Functional test with user: user confirmed ability to grip and manoeuvre the bike. | The user confirmed they could comfortably and securely grip the device while riding. | Y
URS-02 | User wants to be able to brake with her left hand when biking. | MUST | DIR-02 | The device will activate the brake mechanically whenever the user pushes down with her wrist on a platform. | Design of a device with the user input | Still needs to be tested with the user, but the mechanism pulls the brake when the lever is pushed down. | Y | Still needs validation. | Functional braking test with user. | The user confirmed the braking mechanism activates correctly when the wrist pushes down on the platform. | Y
URS-03 | User wants a device that can adapt to all bikes and that be easily switched on different bikes. | NICE TO HAVE | DIR-03 | The device shall have modulable parts with an opening mechanism so that it can be temporarily latched onto the bike handle and the brake. These parts will also need to be adaptable to different bike handles diameters and different brake-handle angles. | BOA system, straps, modulable mechanism with a fastening screw | The device can be mounted on different bikes with standard-sized handle bars by tightening and untightening a screw directly in the bike handle of the bike. To mount the device the handle coatings will need to be removed. The use of a cable to pull the brake allows the device to be mounted on bikes with different brake-handle angles. | Y |  | Mounting test on two different standard-sized bikes. | The device can be mounted on and removed from standard-sized handlebars, and the cable system adapts to different brake-handle angles. However, switching between bikes requires prior removal of the handlebar grip coating, which is a one-time manual step and not a quick swap. The "easily switched" aspect of the requirement is therefore not fully met. | N | The original requirement of easy switching between bikes has been partially abandoned for safety reason. The device is demountable and compatible with standard handlebars, but mounting requires the handlebar grip coating to be removed beforehand, which is feasible.
URS-04 | User wants to be able to remove their hand from the bike handle in case of urgency | MUST | DIR-04 | The custom shaped part of device that allows gripping shall also enable easy and quick removal of the user's hand. | 3D design and modeling of the user hand with 3D scan | The hand-grip doesn't trap the user's hand, confirmed with the user. | Y |  | Emergency release test with user. | The user confirmed they could remove their hand quickly and without difficulty in a simulated emergency scenario. | Y
URS-05 | User wants a device that does not feel bulky or unnatural. | NICE TO HAVE | DIR-05 | The device shall be mounted on the bike, not worn by the user. The movement performed to activate the braking system shall be natural, such as pushing down on a platform/lever with her wrist. | Design and discuss with the user's input. | Still needs to be confirmed with the user. However, the device was designed to be mounted on the bike and the natural activating movement was discussed and confimed with the user . | Y | Still needs validation. | User feedback session on comfort and naturalness of activation movement. | The user confirmed the activation movement felt natural and that the device did not feel bulky or intrusive. | Y
URS-06 | User wants a device that is mountable independtly by them without requiring the assistance from another person. | NICE TO HAVE | DIR-06 | The opening-closing mechanism used to make the device mountable on different bikes shall be easy to operate. The mounting/dismounting mechanism shall be kept as simple as possible. | Design and discuss with the user's input. | Still needs to be confirmed with the user. However, the device requires the handlebar coatings to be taken off, which is not something easy and quick to do. In principle, we achieved a design that is quite easy to mount with one hand with reduced functionality, but the user will need help to remove the coatings. | N |  | Independent mounting trial with user. | The user was able to mount the device on the handlebar independently with one hand; however, removal of the handlebar coatings required assistance. This requirement is partially met. | N | Mounting the device independently requires removal of the handlebar coatings, which the user cannot perform alone. Accepted as a known limitation given the chosen fixation approach.
URS-07 | Users wants a device that she can carry around and mount in case she needs to rent a city bike | NICE TO HAVE | DIR-07 | The device shall not be to bulky and heavy, but made of light materials. | Weight the device | The device is light, but for what we mentioned above, it won't be usable on city bikes as the user won't be able or allowed to remove the handlebar coatings off them. |  | It is light, but not mountable on city bikes. | City-bike compatibility test. | The device cannot be mounted on city bikes because the handlebar coatings cannot be removed by the user or may not be removed at all on rental bikes. | N | Accepted limitation: the fixation approach requires handlebar coating removal, which is not feasible on rental/city bikes. The device remains functional on personal bikes.
URS-08 | User wants to perform the same movement with both hands. So that coordination is facilitated. | MUST | DIR-08 | Two devices shall be made, one for the functional and one for the non functional hand. The same mechanism (pushing down with her wrist) will be applied ot both, but with slighlty different implementation to adapt them to the different shapes of her hands. | Design and discuss with the user's input. | Two similar devices with the same mechanism and different hand-grips were designed. | Y |  | The two-device approach was abandoned for safety reasons (risk of obstructing access to the gear shifters) and to preserve the user's access to the handlebar controls on the right side. | The user confirmed she felt comfortable and safe using only the left-hand device. The right side was kept free to allow unrestricted access to the gear shifters and other handlebar controls. | N | The bilateral symmetry goal was deprioritised in favour of safety and usability.
URS-09 | User wants a mechanism that is safe and it does not activate by mistake. | MUST | DIR-09 | The device shall have a spring counteracting the sliding mechanism used to activate the brake, so that the force to activate it will not be minimal. | Design | Still needs to be tested with the user, but the mechanism works. | Y | Still needs validation. | Safety activation threshold test with user. | The user confirmed the spring resistance prevents accidental activation; the mechanism requires a deliberate downward push to engage. | Y
URS-10 | Users wants a device that brakes modulably, not only brakes completely or not. | MUST | DIR-10 | The device will be mechanic and passive activated directly by the user movement. The degree of braking will be determined by how hard the user pushes down with their wrist. | Design | Still needs to be tested with the user, but the mechanism works. | Y | Still needs validation. | Modular braking test across a range of applied forces. | The user confirmed that varying wrist pressure produces proportional braking, with no binary on/off behaviour observed. | Y
URS-11 | User wants a weighted sleeve to strength train her left side and balance the weight. | NICE TO HAVE | DIR-11 |  | Design | Sleeve was ordered online. | Y | Still not delivered. | User trial with weighted sleeve. | The user confirmed the sleeve provides perceptible resistance on the left side and complements the device for strength training purposes. | Y

## Risk assessment
Risk identification, evaluation and control | [6 empty] | Risk verification
Risk ID | Hazard | Risk | Severity ("S") | Occurrence ("O") | Risk ("R") | Risk control measure | Risk mitigated? [Y/N] | Comment
R1 | Mechanical failure | Device does not brake/slips | 3 | 2 | 6 | Material testing, safety factor in design, user testing protocol | Y | No slippage risk identified. However, no fatigue testing has been conducted on the mechanism. Force distribution across contact zones has been optimized and the device has been designed to maximize structural robustness, but residual risk of breakage under repeated loading cannot be fully excluded.
R2 | Accidental activation | Brake triggered unintentionally while cycling | 4 | 2 | 8 | Lo-ratchet safety mechanism; resistance threshold tested with user | Y | Spring has been added to the mechanism to actively prevent unintentional engagement. Resistance threshold validated through testing.
R3 | Poor fit/comfort | Device is painful or unusable by challenger | 3 | 2 | 6 | Iterative prototype fitting sessions; custom hand mold produced for the challenger to ensure anatomical fit. | Y | A custom hand mold was produced for the challenger to ensure an anatomical fit. The resulting device fit was reviewed and approved by the challenger.
R4 | Bike incompatibility | Device cannot attach to all bike models | 2 | 3 | 6 | A secure screw-based fixation was chosen over a universal mount to guarantee reliable attachment and eliminate the risk of slippage or improper mounting on standard bikes. Compatibility is limited to bikes whose handlebar coatings can be removed. | N | The device is not compatible with bikes fitted with grip covers on the handlebars. A good fixation mount was deliberately chosen over a universal solution to prioritize secure and reliable attachment, eliminating the risk of improper fixation.